## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | QA Team | 2026-01-10 | Missing values in user browsing history dataset causing model training errors | Sprint 1 | Data Engineer | Data Defect | Handled missing values using mean/most-frequent imputation | 2026-01-12 | Closed | Dataset stabilized
2 | QA Team | 2026-01-18 | User-item matrix sparsity leading to poor recommendations | Sprint 2 | ML Engineer | Design Defect | Applied matrix factorization technique | 2026-01-20 | Closed | Recommendation quality improved
3 | QA Team | 2026-01-28 | Low precision score during initial evaluation | Sprint 3 | ML Engineer | Performance Defect | Hyperparameter tuning performed | 2026-01-30 | Closed | Precision increased
4 | QA Team | 2026-02-05 | Delay in recommendation response time under load | Sprint 4 | Backend Developer | Performance Defect | Optimized API and caching implemented | 2026-02-07 | Closed | Meets SLA

## Sheet2
Logical
User Interface
Maintainability
Standards
Others